Construction shall be performed in general accordance with the following sequence:

1.  Prior to beginning of any land disturbing activities, notification and approval must be    granted by Arkansas Department of Transportation indicating that all environmental permits have been obtained. Name of the contact person is-

Kayti Ewing

Natural Resources Division Head

ARDOT

Telephone No.- 501-569-2522.

2. The Contractor shall contact Arkansas “One Call” Center (811 or 1.800.482.8998) before any excavation as required by Arkansas Underground Facilities Damage Prevention Act, §14-271.

3. The Contractor will mobilize equipment and materials to the site using the construction entrances (shown on the plans) along Stoney Point Road. The rock construction entrance shall be constructed.

4. The Contractor shall utilize the haul roads and staging/stockpile areas and will store all equipment and materials in staging areas as shown on the plans.

5. A construction staging area will be established in the vicinity of the access/haul road at the lower end of the project site as shown on the plan sheets. Equipment and materials will be mobilized to this location.

6. The landward side of the haul road and “Limits of Disturbance”, shall be marked with visible stakes and flagging to indicate where equipment should move up and down the project site and where no access shall be allowed.  Temporary safety fence should be installed to delineate the protected wetland area, where no access shall be allowed.

7. Contractor shall not disturb stable sections of the channel, any wetland areas, or other areas outside of the limits of disturbance.

8. There is a small forested area on the property line between the ARDOT property and Mr. Tweedy’ s property, along the north side of the project.  ARDOT or the Engineer will mark the location of the haul road through this forested area, so that there is as little impact to the trees as possible.

9. Wood material (including trees, root wads, limbs and woody brush) should be harvested from the indicated harvest location on the north side of Stoney Point Road.  This material shall be stockpiled along the riverbank in locations where it can be easily accessed for installation, but at the same time does not obstruct grading of the terraces.

10. Enough wood material should be stockpiled on site prior to beginning a new segment of terracing, so that the segment can be completed without delay.

11. Harvested wood material should be kept in as large and intact pieces as possible.  Logs should be at least 10 ft. in length and longer is preferred.  Root wads should have a trunk of at least 10 ft. attached so that they can be anchored into the bank.  Wood should be primarily hardwoods, but softwood trees can be used as fill within the woody fill area.

12. It is important that trees be installed as soon after harvest as possible and before they have time to dry out.

13. Riverbank terracing and woody toe installation should begin at the upstream end of the project and move downstream. Construction should be done in segments of approximately 50-100 linear feet and one segment completed before opening ground and starting the next segment downstream, except for a short transition area.

14. Excavation within the grading limits will be performed so as to limit sediment migration off-site. All stockpiled soil shall have a sediment fence established between the soil and any water body.

15. Do not over excavate; only the soil that needs to be removed should be excavated in order to avoid unstable fill being used to bring the ground surface to grade.

16. Once all materials needed for finishing a segment are stockpiled near the segment, excavation may begin at the upstream end of the project. Excavation of the bank should begin at the elevation indicated and the area to be filled with woody material cut first.

17. Once grading has lowered the bank to the extent needed for access, the dumped riprap toe protection should be placed along the toe of the bank and extended up to the elevation that the woody material will be placed.  Dumped riprap should be placed as shown on the typical sections and details.

18. Once the woody material “pit” is open woody material should be placed into this area, with 3 or 4 feet of woody material extending beyond the bank.  Material should be compacted, and some soil added to fill voids.  It is important that as much of the space be filled with woody material as possible, while being stabilized with some soil fill as needed.  This woody material layer should be 3 feet thick.

19. When the woody layer is filled, the live brush stems should be laid out across the surface with 1 - 2 feet of each stem extending beyond the filled layer.  A light layer of soil can be placed on top of the brush to hold it in place while the coir fiber matting is placed.  Coir fiber matting should be laid on top of the front half of this woody debris layer, so that the width of the matting is aligned upstream to downstream, and the length of the matting can be unrolled up the slope.  This can be done by cutting several 25-foot pieces, so that 3-4 can be installed at a time.

20. Approximately 7-feet of coir fiber matting should be placed over the front half of the wood layer and the rest of the lose matting temporarily placed at the water’s edge.  Then a 1-foot layer of soil should be placed on top of the matting and wood layer.  This should be compacted by the excavator bucket.  Then the lose matting can be pulled back over the soil layer (or lift) enveloping the soil in a “wrap” of coir matting.  The matting should be pinned with hardwood stakes to the top of the soil layer.  The end of the matting should be buried in a trench at the back of the soil layer (lower terrace) and under a live brush fascine to be installed in the same trench.

21. This woody layer installation and creation of the lower terrace should continue downstream until the first segment is complete.  Then the grading of the 3:1 slope, the upper terrace and the final slopes to existing ground can be completed.

22. Once the lower 3:1 slope is graded, coir fiber matting should be applied to this slope and trenched in the upper terrace.

23. Prior to laying any of the matting, the soil surface should be seeded with both the perennial native seed mix and the temporary sediment control seed mix, lightly mulched with straw and then the matting placed and pinned to the soil.

24. The live brush fascine, live stakes, bare-root trees, and any available transplantable trees should be installed if construction is accomplished during the dormant season, fall or early winter.  If construction is not accomplished during the dormant season, then installation of live woody material will need to be done as soon as dormant live material is available.

25. Excavated soil will need to be moved to the upstream disposal area as it is excavated from the bank, so that excess soil does not obstruct work along the bank and does not create an erosion problem.  Soil will be placed on a high ground disposal site at least 50 feet from surface waters. Silt fence shall be placed down slope of the disposal site before soil is moved to the site. This soil will be sloped to match the existing ground.  After the soil is leveled it will be seeded and mulched.

26. Bank and floodplain vegetation, including trees and live stakes, will be installed during the dormant season, November to April.

27. Construction entrances, staging areas and silt fences will be removed once planting is complete.

28. Immediately upon completion of bank grading, the slope will be seeded and covered with Coir Fiber Matting.

29. Upon completion of the riverbank stabilization work, all disturbed floodplain areas including staging areas and haul roads, shall be seeded and mulched. Trees shall be planted in accordance with the planting plan. Permanent seeding mixtures shall be applied as shown on the vegetation plan. Temporary seeding shall be applied in all areas susceptible to erosion (i.e. disturbed ditch banks, steep slopes, and spoil areas) such that ground cover is established within 21 working days following completion of any phase of grading. Permanent ground cover shall be established for all disturbed areas within 15 working days or 90 calendar days (whichever is shorter) following completion of construction.

30. The Contractor shall not disturb stable sections of the channel, any wetland areas, or other areas outside of the limits of disturbance.

31. The contractor shall remove the Haul Road aggregate base course prior to demobilization from the site.

32. The Contractor shall ensure that the site is free of trash and leftover materials prior to demobilization of equipment from the site.