## Project Timeline
CAXXXX PROJECT TIMELINE
DATE | MILESTONE | POSITION | BASELINE | Position Adjusted | Date adjusted | Milestone adjusted
2017-09-01 | Start | 5 | 0 | 5 | 2017-09-01 | Start | Enter dates and an integer for vertical positioning of the date relative to the timeline axis
2017-11-01 | Utilities Complete | 2 | 0 | 2 | 2017-11-01 | Utilities Complete
2017-11-13 | Construction Start | -8 | 0 | -8 | 2017-11-13 | Construction Start
2018-06-26 | Stage 1 Complete | -8 | 0 | 2 | 2018-06-08 | Start - Bridges
2018-06-08 | Start - Bridges | 2 | 0 | -8 | 2018-06-26 | Stage 1 Complete
2018-10-31 | Finish - Bridges | 2 | 0 | 2 | 2018-10-31 | Finish - Bridges
2019-01-07 | Stage 2 Complete | 5 | 0 | 5 | 2019-01-07 | Stage 2 Complete
2019-06-26 | Stage 3 Complete | -8 | 0 | -8 | 2019-06-26 | Stage 3 Complete
2019-08-01 | Stage 4 Complete | -10 | 0 | 5 | 2019-08-01 | Substantial Completion
2019-08-01 | Substantial Completion | 5 | 0 | -10 | 2019-08-01 | Stage 4 Complete
2019-09-09 | Project Complete | -12 | 0 | -12 | 2019-09-09 | Project Complete
|  |  |  | 5 | #NAME?
|  |  |  | 5 | #NAME?
|  |  |  | 5 | #NAME?
|  |  |  | 5 | #NAME?
|  |  |  | 5 | #NAME?

## Project Data Sorted (hidden)
Sort the dates to populate the timeline in chronological order
|  |  | data analysis | [5 empty] | Actual data to chart, which is fed into the Project Timeline worksheet via hidden columns F-H.
| start row | 5 | TIE BREAK | RANK | DATE | MILESTONE | POSITION | NUM | RANK Sorted | DATE | MILESTONE | POSITION
| last entry | 15 | 11 | 1 | 2017-09-01 | Start | 5 | 10 | 11 | 2017-09-01 | Start | 5
|  |  | 10 | 2 | 2017-11-01 | Utilities Complete | 2 | 9 | 10 | 2017-11-01 | Utilities Complete | 2
|  |  | 9 | 3 | 2017-11-13 | Construction Start | -8 | 8 | 9 | 2017-11-13 | Construction Start | -8
|  |  | 7 | 5 | 2018-06-26 | Stage 1 Complete | -8 | 7 | 8 | 2018-06-08 | Start - Bridges | 2
|  |  | 8 | 4 | 2018-06-08 | Start - Bridges | 2 | 6 | 7 | 2018-06-26 | Stage 1 Complete | -8
|  |  | 6 | 6 | 2018-10-31 | Finish - Bridges | 2 | 5 | 6 | 2018-10-31 | Finish - Bridges | 2
|  |  | 5 | 7 | 2019-01-07 | Stage 2 Complete | 5 | 4 | 5 | 2019-01-07 | Stage 2 Complete | 5
|  |  | 4 | 8 | 2019-06-26 | Stage 3 Complete | -8 | 3 | 4 | 2019-06-26 | Stage 3 Complete | -8
|  |  | 2 | 9 | 2019-08-01 | Stage 4 Complete | -10 | 2 | 3 | 2019-08-01 | Substantial Completion | 5
|  |  | 3 | 9 | 2019-08-01 | Substantial Completion | 5 | 1 | 2 | 2019-08-01 | Stage 4 Complete | -10
|  |  | 1 | 11 | 2019-09-09 | Project Complete | -12 | 0 | 1 | 2019-09-09 | Project Complete | -12