## Slide 1: Planning Process
Practical Application

## Slide 2: Types of Exercises
Discussion-Based Exercises
Focus on strategic, policy-oriented issues, and utilizes a facilitator(s) or presenter(s) to lead the discussion
Used to familiarize players with or to develop new plans, policies, procedures, or agreements
MSEL/EEG will be questions asked to gather participants responses
Examples:
  Seminar
  Workshop (WS)
  Tabletop (TTX)
Operations-Based Exercises
Include a real-time response such as initiating roles and responsibilities; and identify resource gaps
Used to validate plans, policies, procedures, or agreements
MSEL/EEG will be action oriented injects to prompt a players response
Examples:
  Drills
  Functional exercise (FE)
  Full-scale exercise (FSE)

## Slide 3: Progressive Exercise Planning Approach
Use a variety of exercises aligned to program priorities and objectives
Increase the level of complexity over time
Does not always imply a linear progression of exercise types
*Information taken from FEMA HSEEP Course

## Slide 4: Building Block Approach to Exercise

## Slide 5: Planning Meeting timeline Review
Concept & Objective Meeting (C&O)
  Conducted 5-7 months before the exercise
Initial Planning Meeting (IPM)
  Conducted 5-7 months before the exercise
Midterm Planning Meeting (MPM)
  Conducted 3 months before the exercise
MSEL Meeting (Optional)
  Conducted 3 months before the exercise
Final Planning Meeting (FPM)
  Conducted 4-6 weeks before the exercise or the exercise plan is due

## Slide 6: Planning Team Members
Typically selected following the C&O Meeting
Members are chosen based on the core capabilities, type of exercise, and draft objectives of the exercise
  They should be subject matter experts for the area they represent on the planning team
    They are not required to know the exercise documents or how to complete them
    Planning team members should not be exercise participants (players)
      Can serve as a controller, evaluator, or SimCell during the exercise

## Slide 7: Exercise Briefings
Senior Leaders Briefing
Controller Briefing
Evaluator Briefing
Actor Briefing
Player Briefing
Observer Briefing

## Slide 8: Activity
C & O Meeting 5-7 months before the exercise

## Slide 9: Concepts & Objective Meeting (Phase 1)
Exercise discussion with elected officials/stakeholders
Identify planning team members
Select mission areas and core capabilities
Fill out the Exercise Notification Form
  Excel Workbook
  Submit completed form to exercise@adem.arkansas.gov
Planning meeting sign-in sheet (Submit with Exercise Notification Form)

## Slide 10: Activity
Initial Planning Meeting

## Slide 11: Initial Planning Meeting (PHASE 2)
Complete the Exercise Overview
  Exercise end date
  Draft SMART Objectives
  Select a threat/hazard
  Scenario
  List the point of contact and how to reach that individual
  Sign-in Sheet

## Slide 12: Activity
Midterm Planning Meeting

## Slide 13: Midterm planning meeting (Phase 3)
Create draft Exercise Evaluation Guides (EEGs)
  One per objective
  Based on local jurisdictional plans, policies, or procedures used for the EEG
Draft the Master Scenario Events List (MSEL) timeline
Draft injects/questions for the MSEL
Develop player briefing
Sign-in Sheet

## Slide 14: Activity
MSEL

## Slide 15: Msel Meeting (Optional)
Review the MSEL
  Make sure the injects/questions are realistic to the exercise
  Make sure the timeline is followed
  Make sure capability targets/critical tasks (from all EEGs) are represented in the MSEL
  Complete the MSEL during this meeting
  Sign-in Sheet

## Slide 16: Activity
Final Planning Team Meeting

## Slide 17: Final Planning Meeting (phase 4)
Review all exercise materials for accuracy
Discuss exercise details
Assign exercise roles to the planning team
  Controller, Evaluator, SimCell, etc.
Submit all finalized planning documents to ADEM Exercise Section by the due date for review
Sign-in Sheet

## Slide 18: Exercise Logistics
Discussion-Based
Facility/room organization
Audio/Visual requirements
Refreshments
Registration/badging
Table/breakout identification
Parking
Operations-Based
Facilities and exercise areas
Audio/Visual requirements
Registration/badging
Parking/Transportation
Actors, Media, Public Affairs, VIPs

## Slide 19: End of exercise activities
Exercise Hotwash
Collect participant feedback forms
Controller/evaluator debriefing
Planning Team debriefing
After-Action Meeting

## Slide 20: Activity
Completing the AAR

## Slide 21: Analysis of Core Capabilities 1
Select the appropriate capability rating
  P,S,M,U
    P = Performed Without Challenges
    S = Performed With Some Challenges
    M = Performed With Major Challenges
    U = Unable to be Performed

## Slide 22: Analysis of Core Capability 2
Assign the Capability Level
  P on Analysis of Core Capabilities 1 = Full Capability Rating
  Any other rating = Partial Capability Rating
Fill in any identified strengths (1 per line)
List any areas for improvement (AFI) identified (1 per line)
Analysis for each AFI
Repeat these steps for every objective

## Slide 23: Appendix A:Improvement Plan
Write a corrective action for each identified AFI
Select the capability element the action aligns with
Make sure the action is assigned to the appropriate organization and POC
Start date of the action
Projected completion date (on-going is not acceptable)

## Slide 24: Sign-in sheet
Every exercise is required to have a sign-in sheet*
  Must contain:
      Exercise name
      Exercise Date
      Agency/organization Name
      Printed name
      Original Signatures
      Email Address
*If a sign-in sheet isn’t complete and turned in with the AAR, the exercise did not happen.

## Slide 25: Submission of AAR
Send the completed workbook to exercise@adem.arkansas.gov for review by the Exercise Section.
  Do not send any exercise materials directly to an individual
Include a sign-in sheet with the workbook submission
  An AAR can’t be processed without an exercise sign-in sheet
All AARs must be finalized by the 90 day deadline for credit to be given

## Slide 26: Recommended Exercise Classes
IS-120.c – An Introduction to Exercises
IS-130.a - How to be an Exercise Evaluator
  Prerequisite: 120.c – An Introduction to Exercises
L-0146 - Homeland Security and Evaluation Program (HSEEP)
  Prerequisite: 120.c – An Introduction to Exercises

## Slide 27: Exercise Resources
ADEM Resources:
  Exercise Templates
  Exercise Trainings covering exercise development and improvement planning
  Exercise Section
  https://www.dps.arkansas.gov/emergency-management/adem/training-exercise/exercise/exercise-resources/
FEMA Resources:
  HSEEP Preparedness Toolkit (Link on ADEM Exercise Page)
  Prep Toolkit
https://preptoolkit.fema.gov/web/guest/user-guide/-/wiki/Main/Registration+and+Sign+In